## Guide
Product Backlog:
- It is a priority list of user requirements to develop a software or an application.
- Product owner owns this document
- Product owner prioritize the user requirements based on the customer feedback or business value
- The user requirements are written in the form of user stories which are explained in detail
- The product backlog is like a repository that act as an input to the sprint backlog.
- In simple sentence, product backlog is simply a wish list for an application.
- Update the product backlog on regular basis
Sprint Backlog
- It is the subset of the product backlog
- Each sprint includes user stories from the product backlog
- Product owner sets the sprint goal for the team
- The team then pick the user stories to fulfill those goals
- The user stories that are moved to sprint are then owned by the scrum team
- It is important to put the sprint goals as static as possible.
- During sprint planning, the team pics the recently prioritized user stories from the product backlog.
- Spring backlog is an output of the sprint planning meeting
User Story
A user story is simply a description of a feature that is described in users own words. Therefore, it is extremely important to recognize the users. A user is the user of a system. When writing user stories, it is also beneficial to explain the business value first.
The user story are written as:
As a (user), I want to ..... so that ......
Examples:
As an administrator, i want to be able to create new user accounts.
As a student, I should be able to upload assignemtns in the Moodle.
As a student, I want to be able to change my password.
Example with business value (recommended)
In order to find the cheapest price, as a buyer i want to compare prices.
In order to check grades in quick time, as a student I want to be able to see all my grades in one page.
Story Points
- They are a unit of measures for expressing an estimate of the overall effort that is needed to implement a produc backlog item.
- The estimation is done by assigning a point value to each item.
- The raw values that is assigned is not important however the relative values matters.
- Let us assume that one of your story is assigend a vlaue 1 and other other story 2. The one with the value 2 means that it requires dobule effort that the story with the value 1. It means the value itself does not matter but the ratios matter.
- When deciding story points, you need to take into account the amount, complexity and any risk or uncertaninty in doing the work.

## ProductBacklog
Product Backlog - Project Title
User Story | Story Point(s) | Priority
|  |  | High | Medium | Low
As a voter, I want to do a query including questions about the election | 4 | 5 | 5 | 3 | 1
As a voter, I want to check all the candidates | 4 | 5
As a voter, I should be able to check results | 3 | 3
As a voter I want a clear interface | 2 | 2
As an admin, I want to add, edit and remove questions | 5 | 4
As an admin, I want to add, edit and remove candidates | 5 | 4
As a candidate, I want to check and change my answers | 3 | 3
As a candidate, I shoud be able to change my picture | 3 | 1
As a voter, I want to save my results | 2 | 1
As a voter, I want to compare my answers with the candidates | 3 | 1
More functionalities to do:
Make logout work
Check that all questions have been answered
Fix bug on making more question breaking result page on questionary
Candidate pictures from database

## sprint_planning_meetings
Sprint Planning | Participants
Week 12 | Jarkko | Lassi | Mikko
Online | X | X | X | Present mark = X
2020-03-24
Week 13 | Jarkko | Lassi | Mikko
Online | X | X | X
2022-04-01
Week 14
Location
Date
Week 15
Location
Date
Week 16
Location
Date
Sprint Planning
- Sprint planning is done at the beginning of each sprint with the participation of the entire scrum team.
- During the sprint planning meeting, the scrum team decides what will be delivered at the end of the sprint by turning the highest priority features on the product backlog into detailed tasks.
- This process creates the sprint backlog.
- The sprint planning meeting focuses on answering two main questions:
1) What needs to be done? and
2) How will it be done?
The sprint goal is also defined during the sprint planning meeting.
Src: https://www.lucidchart.com/

## sprint_backlog_sprint1
Sprint Backlog : Sprint 1
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
As an admin, I want to add, edit and remove questions | 5 | Jarkko
Task : Admin, add questions |  | Jarkko | Ongoing |  |  |  |  | x
Task: Add Login to admin |  | Jarkko | Done | x | x | x
Task : Make database for admin |  | Jarkko | Done | x
Task : Admin, edit questions |  | Jarkko | Done |  |  |  | x
Task : Admin, remove questions |  | Jarkko | Done |  |  |  | x
As a voter, I want to do a query including questions about the election | 4 | Mikko
Task: Make a page for questions |  | Mikko | Done | x
Task: Make a query to fetch questions from database |  | Mikko | Done | x
Task: Added response options for questions |  | Mikko | Done |  | x
Task: Added page for question results |  | MIkko | Done |  | x
Task: Getting questions result from question page to result page |  | Mikko | Done |  |  | x | x
Task: Result page suggesting best candidate/candidates |  | Mikko | Ongoing |  |  |  | x | x
As a voter, I want to check all the candidates | 4 | Lassi
Task : make a page for candidates |  | Lassi | Done | x
Task Fetch information from database to the html site |  | Lassi | Done |  | X
Task Make the page for candidate readable |  | Lassi | Done |  |  | x
Task Add Candidate answers to the page |  | Lassi | Done |  |  |  | x
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0

## sprint_backlog_sprint2
Sprint Backlog : Sprint 2
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
As an admin, I want to add, edit and remove questions | 5 | Jarkko
Task : Admin, edit questions |  | Jarkko | Done |  | X
Task : Admin, remove questions |  | Jarkko | Done | X
Task : Admin, add question |  | Jarkko | Done |  | X
Task: Make a logout for admin pages |  | Jarkko | Postponed
As a voter, I want to do a query including questions about the election | 3 | Mikko
Task: Result page getting scores for best candidate/candidates |  | Mikko | Done | X | X | X
Task: Result page suggesting best candidate/candidates |  | Mikko | Done |  |  |  | X
As a voter, I want to check all the candidates | 4 | Lassi
Task: Find out how to place pictures to database |  | Lassi | Postponed
Task : Add questions to the page |  | Lassi | Done | x
Task
As a voter I want a clear interface | 2
Task: Styling pages |  | Jarkko, Lassi, Mikko | Ongoing |  | X | X | X | X
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0